|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Adama Science and Technology University  School of Electrical Engineering and Computing  Department of Computer Science and Engineering  Computer Science and Engineering Club | | | |  |  |  |
| Weekly activity report | | | | | | | |
| summary | | | | | | | |
|  | | | | | | | |
| Report Date | | WEEK - 2 | Division / responsibility | Prepared By | | | |
| February 28, 2021 | | Feb 22, 2021 – Feb 28, 2021 | President | Mukerem Ali | | | |
| Status Summary | | | | | | | |
|  | | | | | | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Overview | | | | |
|  | | | | |
| task | % Done | Due date | driver | notes |
| **1. Vice President** | | | | |
| Social Media account manage | 70 | Feb 24-28, 2021 | Wendirad Demelash |  |
| Organize our first Family Night | 100 | Feb 27, 2021 | Wendirad Demelash, Mukerem Ali, Mebatsion Sahle, Yohannes Fikru |  |
| **1.1 Public Relations** | | | | |
| Posting Announcements | 100 | Feb 15 - Feb 21, 2021 | Public Relation Members | We have posted  announcements using Social  Media and Hard Papers |
| Announce events for the member and non member students | 80 | Feb 22-28, 2021 | Public Relation Members | Public relation members post event photos ... |
| **1.2 Discipline Committee** | | | | |
| The work is start on this week for to control and manage the lab | 100 | Feb 22-28, 2021 |  | Create Google excel to manage members discipline and punishment |
| **2.1 Competitive Programming Division** |  |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Setting new rules and revising existing rules | 100 | Feb 22 | Mukerem Ali, Mebatsion Sahle | Rules & Division created members of respective division are known.  Assigning heads for subdivisions.  **Andalus**  Ahmed Hibet & Abdi Adem  **Division\_1**  Atsnagn Kifle & Fuad Mohammed |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Orientation for new and existing members | 99 | Feb 22–23, 2021 | Mukerem Ali , Mebatsion Sahle | Promotion was not successful all members was not there but for the attending students the orientation conducted. |
| Discussion with existing members | 100 | Feb 23, 2021 | Mukerem Ali , Mebatsion Sahle | Work load divided for all members |
| **Competitive Programming (ICPC)** |  |  |  |  |
| Divisions created | 100 | Feb 22, 2021 | Mebatsion Sahle | Andalus – 30 members  Division\_1 – 12 (from existing) + 29 |
| Contest for both divisions has begun | 100 | Feb 24-25,2021 | Mebatsion Sahle, Ahmed Hibet, Mukerem Ali, Atsnagn Kifle, Fuad Mohammed | Hard to manage but controllable because there was a lot of people. |
| Curriculum of both divisions is on progress. | 70 | Feb 24 - | Ahmed Hibet, Abdi Adem, Atsnagn Kifle, Fuad Mohammed | **Andalus** Division - It`s hard to determine what to learn and give titles.  **Division 1** – tutorial slides are on progress |
| **Data Science towards AI** | | | | |
| Curriculum designed | 100 | Feb 26, 2021 | Yohannes Melese | - |
| Preparation has been done | 100 | Feb 26, 2021 | Yohannes Melese, Mebatsion Sahle | - |
| Tutorial and practice will start | 100 | Feb 27, 2021 | Yohannes Melese | There is some minor technical faults occurred during the tutorial b/c of shortage of power supply. |
| **Cybersecurity** | | | | |
| Curriculum Designed | 100 | Feb 26, 2021 | Elias Amha |  |
| Tutorial and practice will start | 100 | Feb 28, 2021 | Elias Amha |  |
| Writing Report | 99 | Feb 25-26, 2021 | Mebatsion Sahle |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **3.Development Division** | | | | |
| Dev registrant evaluation | 100 | Feb 23, 2021 | Dev Head |  |
| Android (java) tutorial given | 100 | Feb 26, 2021 | Fuad Mohammed |  |
| Gathering contacts of previous members | 95 | Feb 28, 2021 | Abduselam Hafiz |  |
| Presentation on dev goal, timeline, rules and teams | 100 | Feb 28, 2021 | Dev Head |  |
| Formation of Language league and assigning head for sub divisions to formulate tutorials and workshop outline | 100 | Feb 28, 2021 | Dev head | Lack of data science expert lead to collaboration with icpc data science team |
| Presentation of dev members on their club management system | 72.4 | Feb 28, 2021 | Dev Head | Elias, Bemnet, Atsenag and Mebatsion presented. Nebiyou, Ekram and tehetna didn’t present |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **4.1 Seminar sub-division:** |  |  |  |  |
| Seminar was prepared by Mr. Desta Zerihun | 100 | Feb 24, 2021 |  | The Title was Guide for CSE students |
| **4.2 Video Sub-division** | | | | |
| Video Record for 2020 EthCPC | 80 | Feb 28,2021 | Yonathan Assefa | The problems are solved by Mukerem Ali and on progress to upload on youtube channel |
| **4.3 Tutorial Sub division** | | | | |
| Tutorial for Data Science sub division from CPD | 90 | Feb 27, 2021 | Yohannes Melese |  |

|  |  |  |
| --- | --- | --- |
| **RISK AND ISSUE HISTORY** | | |
|  | | |
| **ISSUE** | **ASSIGNED TO** | **DATE** |
| On Wed, Feb 24, 2021’s Seminar Mr. Desta Zerihun was unable to attend in person, so the seminar had to be conducted through a web platform. |  | Wed, Feb 24, 2021 |