|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Adama Science and Technology University  School of Electrical Engineering and Computing  Department of Computer Science and Engineering  Computer Science and Engineering Club | | | |  |  |  |
| Weekly activity report | | | | | | | |
| summary | | | | | | | |
|  | | | | | | | |
| Report Date | | WEEK – 2 | Division / responsibility | Prepared By | | | |
| February 26, 2021 | | Feb 22, 2021 – Feb 26, 2021 | Competitive Programming Division Head (CPD) | Mebatsion Sahle | | | |
| Status Summary | | | | | | | |
|  | | | | | | | |

As the first week of work, I tried to do works than needs more priority

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Overview | | | | | | |
|  | | | | | | |
| task | % Done | Due date | | driver | | notes |
| Setting new rules and revising existing rules | 100 | Feb 22 | | Mukerem Ali, Mebatsion Sahle | | Rules created, Division created members of respective division are known.  Assigning heads for subdivisions.  **Andalus**  Ahmed Hibet  Abdi Adem  **Division\_1**  Atsnagn Kifle  Fuad Mohammed |
| Orientation for new and existing members | 99 | Feb 22 – Feb 23 | | Mukerem Ali , Mebatsion Sahle | | Promotion was not successful all members was not there but for the attending students the orientation conducted. |
| Discussion with existing members | 100 | Feb 23 | | Mukerem Ali , Mebatsion Sahle | | Work load divided for all members |
| **Competitive Programming (ICPC)** |  |  | |  | |  |
| Divisions created | 100 | Feb 22 | | Mebatsion Sahle | | Andalus – 30 members  Division\_1 – 12 (from existing) + 29 |
| Contest for both divisions has begun | 100 | Feb 24 - 25 | | Mebatsion Sahle, Ahmed Hibet, Mukerem Ali, Atsnagn Kifle, Fuad Mohammed | | Hard to manage but controllable because there was a lot of people. |
| Curriculum of both divisions is on progress. | 70 | Feb 24 - | | Ahmed Hibet, Abdi Adem, Atsnagn Kifle, Fuad Mohammed | | Andalus Division - It’s hard to determine what to learn and give titles.  Division\_1 – tutorial slides are on progress |
| **Data Science towards AI** | - | - | | - | | - |
| Curriculum designed | 100 | Feb 26 | | Yohannes Melese | | - |
| Preparation has been done | 100 | Feb 26 | | Yohannes Melese, Mebatsion Sahle | | - |
| Tutorial and practice will start | - | Feb 27 | | Yohannes Melese | | - |
| **Cybersecurity** | - | - | | - | | - |
| Curriculum Designed | 100 | Feb 26 | | Elias Amha | |  |
| Tutorial and practice will start | - | Feb 28 | | Elias Amha, Kamil Muktar | |  |
| Writing Report | 99 | Feb 25 – Feb 26 | | Mebatsion Sahle | |  |
| Budget Overview | | | | | | |
|  | | | | | | |
| category | spent | | % of total | | on track? | notes |
| **-** | **-** | | **-** | | **-** | **-** |

|  |  |  |
| --- | --- | --- |
| Risk and issue history | | |
|  | | |
| issue | ASSIGNED TO | DATE |
| **-** | **-** | **-** |
| CONCLUSIONS/RECOMMENDATIONS | | |
|  | | |

Planning is helpful for organization.